## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2221-swen-261-07-Bovines
Testing Team Name | fill in when doing cross-team testing

## Test Plan
Sprint 2 User Stories | Acceptance Criteria | Tester initials; date; comments (required if test failed) | Sprint 3 User Stories | Acceptance Criteria | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. |  | As a CUSTOMER I want to see my order after I checkout so that I know the checkout process finished and the OWNER can now see my order in the order page. | Given I have checked out when I clicked check out then I get a confirmation pop-up saying my order is confirmed.
| Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. |  | As a USER I want to log out and keep my shopping cart so that I can return later to checkout or edit my cart. | Given I have items in my shopping cart when I log out and log back in the same items are in my cart.
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. |  | As an OWNER I want to see the orders put in so that I can start fulfilling customer orders. | Given I have an order when the customer has checked out then the order appears on the order page.
| Given that I am on the products page when there are products in the inventory then I see each product and short description. |  | As a USER I want to see a picture of the product that I am looking at so I know what the product looks like. | Given I have a direct URL to an image when enter the link in the "Image URL" textbox, then the image will be linked with the product and will show up to the customer when browsing.
| Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart. |  | As a USER I want to read a description of the product so I know what the product is and does. | Given I have a description of the product when I enter the description into the proper field when creating the product then the user will see the same description when viewing the product
As an OWNER I want to remove products from my e-store so customers don't buy what's not available. | Given a product is out of stock/not for sale when I remove it from the e-store it gets removed from the inventory |  | As a USER I want to see a whole product page so that I know what the product looks like and does | Given the product page has an item when I click on that item then I will be redirected to a new page where the product and information is shown.
As an OWNER I want to add products to my e-store so customers can purchase them. | Given an item I have when I add it to the e-store it shows up in the inventory |  | As a USER I want to log in securely through encryption and decryption so that my data is protected. | Given a user logs in when a username and password is passed to the api then I expect the username and password to be decoded from base64
As a USER/OWNER I want to login to the e-store so that I can buy and sell products. | Given login page when enter my username and password then I expect to be logged into the e-store |  |  | Given a user logs in when a username and password is passed from the api to the url then I expect the username and password to be encoded to base64
| Given i am not a registered user when i click register new user then i should be able to create a new username and be logged in |  | AS a USER I want to edit product qty so that when something is bought the qty goes down. | Given an owner wants to edit the qty when the url for editQuantity is called then the quantity should change.
As an OWNER I want to send a shipping notification when an order gets fulfilled so that the customer knows I have received the order. | Given a user an email is sent to the corresponding email
As a BUYER I want to add products to my shopping cart. | When looking at a product when I click add to cart it shows up in my cart with the qty, and price
As a BUYER I want to remove products from my shopping cart. | Given items in my shopping cart when I click remove they are no longer in my shopping cart.